## Trang tính3
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
index.html | 2022-06-27 |  | 100% | Thu
about.html |  |  |  | Đoan
services.html |  |  |  | Đoan
blog.html |  |  | 100% | Thu
blog-single.html |  |  | 100% | Thu
landing-single.html
contact.html |  |  |  | Đoan
https://demo.w3layouts.com/demos_new/template_demo/03-03-2021/masterwork-liberty-demo_Free/423112365/web/index.html
deadline là 20/7
link vercel deploy: |  | https://masterwork-group9-bc-34.vercel.app/
link ytb |  | https://www.youtube.com/watch?v=AVZwZ3WnxT0
llink srouce code |  | https://github.com/ntlthu/Capstone-Group9-BC34.git
Nguyễn Thị Lệ Thu
Nguyễn Trung Đoan

## Sample
Tasks Name | Start Build | Finish Build | % Build | Names | Start Testing | Finish Testing | % Testing | Names | Notes
Header | 2020-12-10 | 12/13 | 100% | Dev1 |  | 2020-12-14 | 95% | Dev2
Logo |  |  | 50% | Dev A |  | 2020-12-14 | 50% | Nhật Trường
Navbar | 2019-05-23 | 2019-07-01 | 90% | Dev A |  | 2020-12-14 | 90% | Nhật Trường
Submenu | 2019-05-23 | 2019-05-31 | 100% | Dev A |  | 2020-12-14 | 100% | Nhật Trường
Search form | 2019-06-20 | 2019-06-28 | 90% | Dev A |  | 2020-12-14 | 90% | Nhật Trường
Login popup | 2019-06-25 | 2019-07-01 | 80% | Dev A |  | 2020-12-14 | 80% | Nhật Trường
Carousel | 2020-12-10 | 2020-12-13 | 100% | Dev1 |  | 2020-12-14 | 100% | Dev2